{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":85,"n_cols":2,"rows_kept":85,"cut":false,"hidden":false,"merged":[]}
["TIMELINE","Me, Painter, Carpenter, Electrician, Plumber, Drywaller, Heat guy/lawn/misc, Flooring"]
["Aug 27-Sept 7 ","REMOVE and VACUUM ALLLLLL spriders and webs and spider nests!!--- please do not dispose of vaccum contents on premisis. Thank you I love you"]
[null,"Vacuum/clean up basement "]
[null,"Remove all carpet"]
[null,"Remove kitchen cabinets "]
[null,"Remove kitchen laminate floor"]
[null,"Paint basement walls and floor"]
[null,"powerwash and clean exterior to prep for paint"]
[]
["Sept 10-14","Paint exterior "]
[null,"Remove drop ceiling in sun room"]
[null,"Get landscapping quotes"]
[]
["Sept 17-21","Demo guest bath shower"]
[null,"Remove all curtain rods"]
[null,"Remove master bath vanity"]
[null,"Remove master bath mirror, toilet paper holder, towel rack, rod, blinds"]
[null,"Remove master bath shower tile "]
[null,"PAINT TRIM"]
[null,"Remove kitchen subfloor"]
[]
["Sept 24-28","Plumber - install guest bath new shower"]
[null,"Remove bedrooms built in shelving (do NOT remove main floor living room built in shelving)"]
[null,"Remove guest bathroom shelving above toilet "]
[null,"Remove wallpaper in guest bedroom"]
[null,"PAINT TRIM"]
[null,"Electrican - master bed fan, bathroom light, hallway light"]
[]
["Oct 1-5","PAINT UPPER LEVEL WALLS"]
[null,"Get tub reglazed"]
[null,"Hannah - Spray paint master bathroom light (string and base only, not orb) gold, "]
[null,"Exterminator - treat for spiders"]
[null,"Vaccum/clean garage"]
[]
["Oct 8-12","Remove kitchen bulkhead "]
[null,"Carpenter - Remove kitchen back door and kitchen/dining wall"]
[null,"Carpenter - add windows to kitchen"]
[null,"Carpenter - move existing kitchen window to dining room"]
[null,"Carpenter - edit iron railing in kitchen"]
[null,"Carpenter - add siding to back of house where door was"]
[null,"Heating guy - install vent for range hood"]
[null,"Remove tack strip and nail holes where carpet was (living room, stairs, office)"]
[null,"Drywaller - fix kitchen/dining ceiling and wall where wall was removed, as well as window/back door area"]
[null,"Electrican - kitchen rewire, dining light, entry light, gues bath light, sunroom"]
[null,"Paint sun room ceiling white, as well as wood corners in sunroom "]
[null,"Paint back entry laundry cabinets "]
[null,"Paint ceilings if needed (possibly main area because we moved wall)"]
[null,"Sand front door to origninal wood"]
[null,"Clean fireplace and planter"]
[null,"Remove lower level living room shelving and brackets"]
[null,"Lanscapping - bobcat remove ground cover"]
[null,"Hannah - install guest bath floor tile"]
[]
["Oct 15-19","Carpenter - install trim around new windows in kitchen "]
[null,"Carpenter - put laundry cabinet doors back on, but change the direction/hinges of the middle two doors "]
[null,"Carpenter - replace garage entry door"]
["************","Carpenter - Install kitchen cabinets "]
[null,"Carpenter - install new guest bath vanity "]
[null,"Carpenter - Install new bathroom mirrors "]
[null,"Carpenter - Install new master bathroom vanity "]
[null,"Carpenter - install hardware, towel bars, curtain rods, etc. "]
[null,"REMOVE TREES?"]
[null,"Carpenter - install laundry new cabinet "]
[null,"Fill nail holes in trim, sand, and touch up paint "]
[null,"Plumber - Remove laundry sink "]
[null,"Flooring - LVT"]
[null,"Weed killer driveway "]
[null,"Hannah - tile master bathroom shower walls "]
[null,"Ty - sheetrock garage"]
[]
["Oct 22-26","Deliver appliances"]
[null,"TY AND HANNAH - CONDO CLOSING DAY!"]
[]
["Oct 29-Nov 2","Flooring - carpet (lower level family room and stairs, upper level office)"]
[null,"Plumber - install bathroom faucets and toilets"]
[null,"Carpenter - add shoe moldings"]
[null,"Carpenter - hang range hood "]
[null,"Fill nail holes on new trim, sand, and touch up paint "]
[null,"TY AND HANNAH - MOVE IN 10/30!!!! YAY!!!!"]
[]
["Nov 5-9","Premier -  countertops "]
[null,"Flooring - hardwood"]
[null,"Plumber - install faucet, dishwasher, fridge"]
[null,"Hannah install kitchen backsplash"]
[null,"Chimney sweep and inspection"]